## Risk Register
Asset | Threat | Vulnerability | Likelihood | Impact | Risk Level | Proposed Control | NIST CSF Category | Control Justification
AWS S3 bucket with patient health data | Unauthorized data access | No bucket policy or encryption enforced | High | High | High | Enable S3 encryption and restrict bucket policies | PR.DS | Encrypts sensitive patient data and restricts public exposure—essential for HIPAA compliance and baseline AWS hardening.
Employee laptops (remote work) | Lost/stolen device | No disk encryption, no device tracking | Medium | High | High | Mandate disk encryption and install EDR | PR.IP | Addresses data loss risks by ensuring devices are protected if misplaced or stolen. EDR improves detection of compromise.
Web application login system | Brute-force attack | No rate-limiting or MFA | High | High | High | Add MFA + rate limiting to login endpoint | PR.AC | Limits account abuse and prevents credential stuffing. MFA and rate-limiting are fundamental access controls.
Internal documentation on Google Drive | Insider access abuse | Excessive permissions | Medium | Medium | Medium | Review and limit Drive permissions | PR.AC | Minimizes internal data exposure and enforces least-privilege principles in collaborative platforms.
3rd-party analytics integration | Data leakage via weak integration | No security assessment of API | Medium | High | High | Conduct 3rd-party risk assessment and enforce API gateway | ID.RA | Ensures third-party access meets internal security standards. Reduces data breach exposure through API hardening.

## Analysis Summary
Section | Details
Risk Prioritization Method | Risks were rated based on a qualitative likelihood × impact matrix. 'High' risk entries reflect both high exploitability and organizational impact.
Top Risks | - AWS S3 bucket storing patient data - Web application with weak login security - Employee laptops with no disk encryption
Top Controls Implemented | - S3 encryption & restricted access policies (PR.DS) - MFA + rate limiting for web login (PR.AC) - Disk encryption & EDR on remote devices (PR.IP)